## VIOLENCE AGAINST WOMEN, DOMESTIC ABUSE AND SEXUAL VIOLENCE (VAWDASV) CORE AND PERPETRATOR SERVICES REVENUE GRANT – ## PROGRESS REPORT AND CLAIM FORM 2021-22 Period of report and claim; Period: Q3 2021-22. Before you claim - This form should be read in conjunction with your award letter, which contains the conditions which determine how your grant will be paid - Your claim cannot be considered for payment unless all the required information listed below is present - The Welsh Government reserves the right to seek further information in support of the claim and withhold payment until all such details are supplied.; - Check your expenditure covers those areas outlined and agreed within the Delivery Plan, Annex A and Annex B. - Only expenditure that has a full audit trail to prove defrayment can be claimed. You will be certifying that you have checked and approved all expenditure, including the audit trail for each organisation included in this claim. - If activities outlined in the Delivery Plan are delayed, write in good time giving a full explanation to be considered by this office.. SECTION 1: CONTACT DETAILS Region:; Mid and West Wales. Name and contact details of Lead Officer within the Regional Partnership Name of the Accountable Body (Regional Banker); Natalie Hancock Mid and West Wales Regional VAWDASV Adviser nhancock@carmarthenshire.gov.uk Tel: 07392317137 Carmarthenshire County Council agreed as Regional Banker. The signed claim should be returned to: Violence against Women, Domestic Abuse and Sexual Violence Team Community Safety Division Welsh Government Rhydycar, Merthyr Tydfil CF48 1UZ via the VAWDASV mailbox VAWDASV@gov.wales.

OVERVIEW OF ACTIVITY PROGRESS

- Summary of progress in delivering the activities outlined in your Delivery Plan during the period of this claim:

Survivor engagement We will; Intended Outcomes; Progress to date; Next Steps. Develop a reginal framework for survivor engagement; A regional VAWDASV survivor engagement framework Survivors have a consistent, cohesive mechanism to have their voices heard and to inform policy and practice improvements.; Task and finish group is established with reviewed membership. We are working with a consultant toward establishing intended regional framework, including a survivor advisory panel. This has included facilitating several engagement activities and sessions with survivors to inform the regional framework and our Regional Logo.; Partnership Coordinator to lead on next steps to develop and engage with existing engagement frameworks within MWW, including HDUHB and DPP. Focus on developing the Regional Survivors Advisory Panel.. Governance and leadership We will; Intended outcomes; Progress to date; Next Steps. Establish a mechanism to monitor and evaluate the strategy and its effect; An agreed set of outcomes, aligned to the National Strategy, that measure the progress and success of the strategy An agreed Regional Data Set that supports the monitoring framework; An agreed set of regional outcomes is in place. Regional Adviser represents the region on the National Strategy Review and Consultation work; Regional Indicators to be reviewed in line with the National Strategy review. This is include within our draft 2022-23Delivery Plan. MWW Regional Strategy will be reviewed in line with the new National Strategy in 2022-23.. Align Regional Framework for the commissioning, quality assurance and oversight of DHRs with the Single Unified Safeguarding Review (SUSR); A consistent framework for the commissioning, quality assurance and oversight of DHRs across the region; Regional Adviser and several members of the VAWDASV Strategic Board are members of the SUSR task and finish groups.; Regional representative will support implementation and continue to update on progress of the SUSR process.. Strategic Priority 1 – Increase knowledge and awareness and challenge attitudes towards equality and domestic abuse, sexual violence and violence against women amongst citizens of Mid and West Wales We will; Intended outcome; Progress to date; Next Steps. Develop a clear VAWDASV communication strategy, informed by survivors and stakeholders that will support coordinated and consistent messages for individuals, families, professionals, employers and communities; A regional communication strategy Consistent regional messaging for VAWDASV and Equality Communication strategy that is informed and supported by evidence and resources; Task and finish group is established. We are working with a consultant toward establishing intended framework, which will inform Communication plans annually. We have delivered two regional campaigns, in partnership with the RSB, in line with NSW. These campaigns focussed on Older Victims of DA and bystander work within the Beauty Industry. We have a Regional resource and key communications POC map established. Our regional DHR materials are completed and were launched on the RSB website during NSW. The region has also been working on our Regional Branding, informed by survivors. Draft designs went to the Delivery Group for consultation and the final design has now been agreed.; Continue to develop the framework supported by the survivor engagement framework. Final design for the Regional Logo will now be shared at the Strategic board and Delivery Group in January. We are currently in the process of establishing a Regional Survivor Advisory Panel to oversee all the planning for engagement activities, and decision making in terms of the development of the regional network. Once established, the Regional Survivor Advisory Panel will work towards piloting a Survivor peer support group in one local authority area. In addition, we are currently working with survivors to support Carmarthenshire County Council’s re-commissioning work, and to support Dyfed Powys Police to understand and learn from Survivor’s experiences of Police involvement in relation to their domestic abuse and sexual violence experiences. The Regional Survivor Advisory Panel will support the establishment of a Dyfed Powys Police VAWDASV Survivor Forum, to address some specific questions.. Strategic Priority 2: Increase awareness of children and young people of the importance of safe, equal and healthy relationships and that abusive behaviour is always wrong We will; Intended outcome; Progress to date; Next Steps. Produce recommendation report to Strategic Board, outlining best practice delivery of healthy relationships support and education in formal and non-formal settings.; Recommendations report to the Strategic Board and Safeguarding Executive; We’re currently working with Public Health Wales and the regional Healthy Schools advisors to create a regional VAWDASV Resource Directory. We are also currently working with Welsh Government to make Group 1 E-Learning training available to School Staff via HWB. We now sit on the Regional Strategic Group for Whole School Approach to Emotional and Mental Wellbeing and we will be overseeing all work in relation to VAWDASV and the new curriculum via this regional platform. We are also involved in 3 Advisory Groups for Pembrokeshire, Ceredigion and Carmarthenshire. We’ve been working with Welsh Government, NSPCC and Welsh Women’s Aid to create a Children and Young People specific Consultation on the new VAWDASV Strategy. We’re supporting Dyfed Powys Police to undertake a regional mapping exercise of the support services available to Children and Young People.; Establish a separate Group to include our regional Specialist Service Providers to support the implementation of the new curriculum on a regional and local level. We will work with our Specialist Service Providers and Education Colleagues in each of the 4 Local Authority areas to create Local pathways to specialist VAWDASV support for Schools. In February and March we will be taking part in workshops with Heads of 24 schools across the region to identify areas of concern in relation to the new curriculum. We will use these and future workshops as a platform to communicate directly with schools and address concerns specific to VAWDASV. We will support the consultation on the new WG Strategy by sharing the Consultation document with our Regional Partners and co-facilitating online workshops with Children and Young People, to ensure that the voices of Children and Young People in Mid and West Wales are heard. Continue to support DPP with a series of CYP engagement workshops to gain a better understanding of Children and Young People’s experiences.. Agree a monitoring framework that will enable the region to meet reporting requirements contained within the Act; Monitoring framework in place to enable the region to meet reporting requirements within the Act. Strategic Priority 3: Increase focus on holding perpetrators to account and provide opportunities to understand their behaviours and consequences of their behaviours based around victim safety We will; Intended outcome; Progress to date; Next Steps. Ensure a Regional Offer of Perpetrator Intervention consistently across Mid and West Wales; Equality of access to Perpetrator Programmes, focussed on improving victim safety, consistently across the region communities we work with; Regional Provision available across Mid and West Wales is now live. Monthly monitoring is also in place to analyse data and evidence to inform future funding options. DPP Vulnerability Hub post will support this regional initiative.; Review of regional offer to inform future commissioning arrangements for this provision. Implementation planning across successful funding awarded via OPCC to expand provision and include elements of; CYP, CPA and align with work of the vulnerability hub. Strategic Board to decide on Regional approach to funding existing provision post March 2022.. Embed the work around the Stalking Perpetrator Intervention, within current practice; Specific Stalking Intervention and identification framework embedded sustainably within the region. Implement research findings to outline our regional approach to developing interventions aimed at female perpetrators; Bespoke development of specific intervention aimed at females identified as perpetrators, in response to specific MWW need. Strategic Priority 4: Make early intervention and prevention an integrated priority in Mid and West Wales We will; Intended outcome; Progress to date; Next Steps. Increase earlier identification of individuals who are experiencing VAWDASV and appropriate signposting, referrals and safeguarding by increasing awareness of VAWDASV amongst GPs working across Mid and West Wales; Pilot Project for delivery of IRIS in Mid and West Wales; Agreed resourcing of and project implementation plan for an IRIS pilot in Carmarthenshire, via HDUHB; Tender is now live for Advocate Educator role across Carmarthenshire.. Develop and improve the Regional identification, response and reporting of Child to Parent Abuse across Mid and West Wales; Consistent and robust Regional Response to CPA that is aligned to HO guidance.; Regional CPA Policy 3rd draft has gone to the Regional Policies and Procedures Subgroup. Regional Pathway to Support for CPA specific support and intervention is also now live. Regional CPA training and PRAM Pilot and evaluation is now complete.; Redraft CPA Policy to be signed off and circulated. Regional CPA training to be extended.. Strategic Priority 5: Relevant professionals are trained to provide effective, timely and appropriate responses to victims and survivors We will; Intended outcomes; Progress to date; Next Steps. Oversee, monitor and review the regional implementation of the National Training Framework ensuring compliance by professionals in relevant authorities and supporting the specialist sector to achieve Groups 2-5; Centralised coordination and reporting framework for the delivery and monitoring of the Regional Training Plan Implementation of Groups 1 and 6 to staff across Relevant Authorities Implementation of Ask and Act to relevant staff across the region Support the specialist providers to achieve groups 4 and 5 under the National Training Framework; Consistent Regional Training plan and reporting mechanism is live within the Regional VAWDASV Training Subgroup. We have been awarded additional funding to support delivery, which has been allocated within the Regional VAWDASV Training Subgroup. We have invested in Groups 4 and 5 across our specialist service providers.; Continue to work with the training leads to increase compliance with the NTF. Expand on delivery via resourced increased capacity. Focus on Group 6 for the 2022-23 Delivery Plan.. Strategic Priority 6: Provide victims with equal access to appropriately resourced, high quality, needs led, strength based, gender responsive services throughout the region. We will; Intended outcome; Progress to date; Next Steps. Review existing commissioning arrangements to inform the development of a joint, integrated “one public service” commissioning strategy; Established Regional Commissioning Subgroup Consistent VAWDASV Service Specification operating across the region. Joint commissioning activities, in relation to VAWDASV specific services, delivered across MWW.; Regional VAWDASV Service Specification is now in place. We have delivered individuals sessions with each LA commissioning team and IPC, to map exiting provision against the specification.; Each LA is now carrying out actions agreed within the individual sessions, to work towards implementation of the service specification. Regional Adviser and Partnership Coordinator to support LA’s in recommissioning activities. Continued consideration for potential cross boundary commissioning exercises. VAWDASV Strategic Board to consider commissioning actions from Regional DHRs..

- Provide confirmation that the Regional Partnership is on course to deliver in line with the Delivery Plan, and/or provide details of any problems or issues encountered for the period of the claim and how these have been managed:

As outlined above, we are making progress against all identified delivery within the 2021-22 Delivery Plan.

- Details of any key risks identified for the next quarter and how these will be mitigated:

None

DELIVERY OF OUTCOMES AND WORK PROGRAMME

Provide an update on progress in delivering each of the activities outlined in the work programme included in sections 2 – 5 of your Delivery Plan, during the period of this claim.  Include how these link to the delivery of the Welsh Government’s strategic priorities to reduce the incidence of violence against women, domestic abuse and sexual violence as outlined below:

  - promote awareness of, and to prevent, protect and support victims;

  - strengthen the strategic leadership and accountability for violence against women, domestic abuse and sexual violence; and

  - improve the consistency, quality and join-up of service provision in Wales.

- PROGRESS REPORT

Commissioning VAWDASV Services. What services have been delivered in the region, including responsibilities?; The MWW Regional IDVA Service is the only service delivered and resourced directly from the VAWDASV Grant. The Service is Commissioned jointly via the OPCC and Regional Grant. Hafan Cymru and Pobl deliver the contract which has been in place since 2018.. Provide an update on the how the region’s needs assessment is impacting on services.; The 2018 MWW Regional VAWDASV Strategy was informed by an initial assessment of need and current provision in the region as well as the wider wellbeing and population plans throughout Mid and West Wales. The work around our Regional Commissioning Strategy included work to further assess the need for provision across the region in response to VAWDASV. The result of this work included producing our Regional Commissioning Document and Regional Service Specification, which informed a gap analysis in relation to our current provision offer. The above mentioned pieces of work continue to underpin the work of the Regional Partnership and inform our annual delivery plan objectives. We are now supporting the population needs assessment work across the region. This will inform the review of our regional strategy in line with the reviewed Welsh Government National Strategy. Our 2022-23 clearly outlines how we intend to commission a full review of our Regional Needs Assessment and VAWDASV Strategy in the early part of 2022, enabling us to launch a new Regional Strategy in 2023-24.. Provide an update on gap analysis.. Provide details on how a continued and consistent service for service users has been ensured.; Following the work around our approach to Commissioning, all commissioning activities are now overseen by the MWW Commissioning Subgroup. This will ensure that all activities will consistently meet the Welsh Government guidance in terms of Commissioning VAWDASV Services. Our 2022-23 Delivery also captures how we will support the review of this guidance, ensuring this is captured within the VAWDASV commissioning activities across MWW. Our regional commissioning document recognises the importance of consideration given to continuation and consistency of service provision for survivors across MWW. This is also included within our Regional Service Specification. We also carried out a survivor consultation based on how we can best maintain service delivery, while looking at recommissioning services across the region. This will be used to inform re-commissioning activities across the region.. Provide details on how the Regional Partnership has provided support for all service user groups.; The work of the regional survivor engagement and communication subgroup are clear on the need for us to be innovative and creative in how we engage with the diverse groups and communities across the region. This approach is consistent and will underpin the work within all of our regional work and delivery plan. The representation of survivors and their experiences is central to our approach. We aim to explore diverse options for engagement, that are unique and effective in capturing the needs of the population across the region. This will inform and underpin the work we have commissioned to complete in line with the development of our Regional Survivor Engagement Framework. We continue to carrying this forward within our Regional Communication and Engagement subgroup and have delivered engagement sessions progressing work within this area.. - Partnership and Collaboration. Provide an update on the collaboration development of the Regional Partnership Board; The MWW Regional Partnership commissioned an independent review of the governance arrangements around the Regional Strategy in 2019. The resulting recommendations were accepted by the Board and saw a review of the TOR and membership of the Regional Strategic Board and the development of the Delivery Group. These arrangements have now been in place since October 2019 and are working well. The coordinated response to Covid-19 and work on recovery post-pandemic, across the region, is evidence of this and how effective the partnership has become. Within the Reviewed National Strategy Consultation Document, it discussed how Regional Boards will be reviewed in line with the implementation of the National Partnership Board. This will be supported across MWW by the Regional Adviser.. Provide an update on collaboration with other stakeholders (Police, PCCs, education services, housing organisations, HMPPS and non devolved crime and justice agencies; The Regional governance review strengthened the membership and collaboration with key stakeholders across the region. Membership of the VAWDASV strategic group includes representatives from all relevant authorities including; - All four local authorities - Dyfed Powys Police - OPCC - Both health boards - Business Manager from the Regional Safeguarding Board Three nominated representatives from the specialist sector - NPS - CSPs As well as the three specialist provider reps on the strategic board, all providers are individually invited to sit on the Delivery Group. The specialist providers forum also meet prior to the Strategic Group to discuss the papers and feed back directly to the Regional Adviser. As Regional Adviser I also sit regularly on; each of the Local Authority Safeguarding Operational Groups in each of the four areas where I deliver a full update report. The membership of the Delivery Group also goes further and includes partners such as; YOS, Education Safeguarding Leads and research projects.. Provide an update on partnership working (Third sector, specialist VAWDASV services, survivors, service users); As identified above, the partnership with the specialist sector in and around our regional strategy is very strong. The Specialist Sector Providers are core to our Regional Strategic Board and Delivery Group. We have specialist sector reps as Deputy Chairs on both boards and the sector are well represented at each meeting. We are also working hard within our Communication and Engagement Group, as well as all areas of the Delivery Plan, to ensure the experiences of survivors are key and underpin the whole regional plan. The work we have commissioned, with an independent consultant, on the development of our Regional Survivor Engagement Framework will also look to build and improve on this. We already have an established group of survivors who we are consulting with on regional projects such as commissioning and branding and commissioning. This is also further by the development of our Regional Survivors Advisory Panel.. - Awareness, Promotion and Education How has your region:. promoted information and awareness-raising campaigns including, but not exclusively to the Live Fear Free helpline?; The Regional Partnership supports the Welsh Government Communication strategy and its awareness raising campaigns via our whole Reginal Partnership and the extended networks. As Regional Adviser and Regional Partnership Coordinator, we are part of the Welsh Government Communications Subgroup and have fed into the development of the National Campaigns and how these are supported via the Regional Partnership. The MWW Regional Communication Strategy and our survivor engagement framework is being developed via the established subgroup and with support from a specific commissioned piece of work looking at best practice and existing processes. We have included the Welsh Government Communication Campaigns within our communications calendar, NSW communications plans and our targeted communications work such as the campaign aimed at the beauty industry. We have delivered two regional campaigns, in partnership with the RSB, in line with NSW. These campaigns focussed on Older Victims of DA and bystander work within the Beauty Industry. We have a Regional resource and key communications POC map established. Our regional DHR materials are completed and were launched on the RSB website during NSW. The region has also been working on our Regional Branding, informed by survivors. Draft designs went to the Delivery Group for consultation and the final design has now been agreed.. worked towards a whole school approach to healthy relationships and worked with Hafan Cymru to promote and deliver the Spectrum programme?; Hafan Cymru and the four local authority Education Safeguarding leads are represented on the regional partnership and specifically on the Delivery Group. We’re currently working with Public Health Wales and the regional Healthy Schools advisors to create a regional VAWDASV Resource Director. We are also currently working with Welsh Government to make Group 1 E-Learning training available to School Staff via HWB. We now sit on the Regional Strategic Group for Whole School Approach to Emotional and Mental Wellbeing and we will be overseeing all work in relation to VAWDASV and the new curriculum via this regional platform. We are also involved in 3 Advisory Groups for Pembrokeshire, Ceredigion and Carmarthenshire. We will next establish a separate Group to include our regional Specialist Service Providers to support the implementation of the new curriculum on a regional and local level. We will work with our Specialist Service Providers and Education Colleagues in each of the 4 Local Authority areas to create Local pathways to specialist VAWDASV support for Schools. In February and March we will be taking part in workshops with Heads of 24 schools across the region to identify areas of concern in relation to the new curriculum. We will use these and future workshops as a platform to communicate directly with schools and address concerns specific to VAWDASV. We’ve been working with Welsh Government, NSPCC and Welsh Women’s Aid to create a Children and Young People specific Consultation on the new VAWDASV Strategy. We will support the consultation on the new WG Strategy by sharing the Consultation document with our Regional Partners and co-facilitating online workshops with Children and Young People, to ensure that the voices of Children and Young People in Mid and West Wales are heard. We’re supporting Dyfed Powys Police to undertake a regional mapping exercise of the support services available to Children and Young People.. - Monitoring and Evaluation. Update on monitoring arrangements.; We have clear reporting arrangements via the governance structure around our regional strategy. As Regional Adviser I monitor and report on our progress against the Regional Delivery Plan at several points throughout the financial year via; - The Regional Safeguarding Board- Full Quarterly RAG Rated reports - The Regional Strategic VAWDASV Board- Full Quarterly update reports. - The Delivery Group- Bi-monthly progress update reports - The Four Local Authority Safeguarding Group meetings- Quarterly progress update reports We also have reporting arrangements with the four PSB leads via the CSPs and directly into the LCJB and CJIW.. Update on plans to evaluate performance against the delivery plan; As outlined in the strategy and regional delivery plans, we aim to review our own Regional Indicator Set that measures the impact of the Regional Strategy and the difference the strategy is making. This will also be informed by a Regional Data Set. The Welsh Government VAWDASV Reviewed National Strategy is now out for consultation. Review of the National Indicators is included within the reviewed strategy. We will support Welsh Government in reviewing these indicators to ensure they reflect the new strategy. Following this, and following review of our Regional Strategy, we will review our existing Regional indicator set..

| - OUTCOMES AND OUTPUTS |  |
| --- | --- |
| Details of the outcomes/outputs achieved in this reporting period | The MWW Regional VAWDASV Grant contributes towards the commissioned regional IDVA service. This is the only direct service provision that the grant funds and therefore the outcomes and outputs relate only to the IDVA service which has only been operating since 2018. 64% of the VAWDASV grant contributes to this direct service provision but the grant itself accounts for only 50% of the annual service contract price. The outputs in relation to this service are detailed below. |

PLEASE ONLY COMPLETE THE FOLLOWING TABLES THAT RELATE TO YOUR DELIVERY PLAN?

Further narrative about how beneficiaries have been supported can be added here if required:

- CLAIM INFORMATION

- Provide details of actual expenditure in relation to the Welsh Government VAWDASV Grant [Note: this information should reflect the breakdown of costs  set out in your Delivery Plan]

| Activity | Level of cost of activity (forecast spend) | Level of funding from VAWDASV Grant |  |  |  | Funding from other sources: source and amount | Total actual spend to date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Period 1 £ | Period 2 £ | Period 3 £ | Period 4 £ |  |  |
| Regional Adviser | £53,085 | £13,500 | £13,500 | £13,500 |  |  | £40,500 |
| Regional Partnership Coordinator | £46,000 |  | £23,000 | £11,500 |  |  | £34,500 |
| Regional IDVA Service | £199,974 | £49,993.50 | £50,000 | £50,000 |  |  | £149,993.50 |
| Priority 1 | £7,000 |  | £1,050 | £3,850 |  |  | £4,900 |
| Priority 5 | £5,000 |  |  | £4,800 |  |  | £4,800 |
| Priority 6 | £4,000 |  | £3,950 |  |  |  | £3,950 |
| Regional branding |  |  |  | £8,500 |  |  | £8,500 |
| Totals | £325,926 | £63,493.5 | £91,500 | £92,150 |  |  | £247,143.50 |

- Please update your indicative spend profile for the level of grant awarded:

| Period | Indicative Spend | Actual Spend |
| --- | --- | --- |
| Period 1: April to June | £81,481 | £63,493.5 |
| Period 2: July to September | £87,476.83 | £91,500 |
| Period 3: October to December | £87,476.83 | £92,150 |
| Period 4: January to March | £87,476.83 |  |
| Total Spend: |  | £247,143.50 |

- GRANT CLAIM

| TOTAL GRANT ALLOCATION APPROVED: |  |  |  |  |
| --- | --- | --- | --- | --- |
| FINANCIAL YEAR 2021 - 2022 | (Apr-Jun) £ | (Jul-Sept) £ | (Oct – Dec) £ | (Jan-Mar) £ |
| AMOUNT CLAIMED TO DATE | £63,493.50 | £91,500 | £92,150 |  |
| CUMULATIVE AMOUNT CLAIMED TO DATE | £63,493.50 | £154,993.5 | £247,143.50 |  |

| FORECAST EXPENDITURE FOR FY 2021 - 22 | £325,924 |
| --- | --- |
| GRANT STILL OUTSTANDING / UNDERSPEND FORECAST: | £ |

If there is underspend, please provide an explanation as to how this has occurred and any proposals for reallocating the funding.

- Please provide an update for each SMART aim, objective and outcome for perpetrator services;

Aims/ Objectives and Outcomes of the Pilot. Specific; Measurable; Achievable; Realistic; Progress. Agree Contribution from all Regional Partners; Regional Partnership Agreement in place for the resourcing of Regional Perpetrator Intervention offer; Proposal will go to VAWDASV Board on 27th January for discussion and agreement; Partners have been briefed on the proposal in previous meetings and are fully aware of the intended action; Complete- agreement in place. Project implementation plan for the roll out and communication of extension to the existing Perpetrator Intervention provision; Agreed Project Implementation Plan and Regional Communication; Existing provision is being delivered and is extendable; Discussion around extension of provision beyond March 2021 has been had with existing providers; Complete- Extension of provision in place. Content for Press Release and supporting media to be agreed and released; Intervention Hub to draft press release and media documents for team to comment on and agree content.; Intervention Hub have templates to work from. Content will be agreed with all partners coordinated by Regional Adviser; Intervention Hub have experience in this area. Regional Adviser has established effective working group.; Complete- press release circulated. SLA to be agreed with the Intervention Hub in relation to the license; SLA to be agreed and signed by agreed parties; Intervention Hub have drafted the SLA; The region has an existing SLA already in place; Complete- SLA in place. Choices programme to be delivered across the Region; Intervention to be monitored quarterly to measure numbers engaged; Regional delivery is already in place and will be extended in to 2021-22; This is manageable with the identified staffing hours; Complete- Choice is now being delivered across MWW. Intervention Hub delivered across the Region; Monthly Management reports to be provided; Regional delivery is already in place and will be extended to 2021-22; This is manageable with the identified staffing hours; Complete- IH is now being delivered across MWW. Project implementation plan for the continuation of the stalking perpetrator intervention; Professor Jane Monkton-Smiths evaluation document with outline key recommendations; The Regional pilot will guide regional expansion and extension of the provision; The Regional pilot has indicated the specific need and demand for the region and this has been costed in terms of staff hours; Evaluation is complete. Delivery of the Stalking Perpetrator Intervention across MWW; Intervention to be monitored quarterly to measure engagement; The provision is currently being delivered within the region and will be extended in to 2021-22; This is manageable with the identified staffing hours; Complete- Delivery of the intervention has been extended. Project plan for the data project with Marianne Hester and DPP; Project plan for the intended improvement of data capture and analysis; Marianne has been working on this area within our reginal subgroup throughout 2020-21 and has submitted a bid in partnership to the HO; The Regional Subgroup have done a significant amount of work around this specific are and the HO project will also support this research; This area of the action plan is not being carried forward at this stage as we were unsuccessful with HO funding.. Deliver Female Perpetrator Data Improvement and Analysis project with Marianne Hester; Data analysis and recommendation report.

- Please provide an update of how the activities link to existing VAWDASV regional provision and contribute to Welsh Government’s VAWDASV strategic priorities outlined for perpetrator services;

• Establish an understanding of ‘what works’ with VAWDASV perpetrators We have worked closely with Forensic Psychology UK (FPUK), Threshold DAS, MFCC and Calan DVS on the development of this proposal. Threshold DAS currently deliver the only Respect accredited Perpetrator intervention within MWW and MFCC and Calan DVS are currently delivering the Intervention Hub pilot across the region. FPUK have also worked with us in the development of the stalking perpetrator intervention and have been delivering on the pilot provision. The specific needs of MWW; in terms of large geographical areas, dispersed communities and lack of provision for perpetrators, means that there is little research and knowledge of what works for the region in such a specific provision of service. These pilots have provided us with valuable insight into the effectiveness of theses interventions, the engagement from individuals referred and the mechanisms by which we can make these interventions accessible in a largely rural area and with the specific barriers faced by communities within MWW. • Inform the commissioning of effective and sustainable VAWDASV perpetrator services There are currently no commissioned Perpetrator Services across MWW. In line with the work of the MWW VAWDASV Commissioning Subgroup, the regional pilots have allowed us to explore the requirements of a commissioned service within the MWW region and what considerations we will need to factor into a longer-term contract. The pilots provided evidence and examples of best practices and lessons learned to be incorporated into our Regional Commissioning planning. This will be specific to the needs of the MWW region, it’s communities and in response to the rural barriers to access to intervention that have impacted on the sustainability of similar services delivered in the past. This proposal also means a commitment from the whole partnership in securing a regional offer of perpetrator intervention accessible across Mid and West Wales. • Develop prevention and early intervention approaches As highlighted earlier, the need for these interventions are specifically relevant to learning from DHRs across the region. The lack in such provision has meant that there has been a lack of response to addressing the abusive behaviour of perpetrators earlier on. This is specifically relevant to the Mid and West Wales area, given its rural geography and evidenced by the recent DHR learning. This regional provision is included in regional DHR action plans which identify specific missed opportunities in offering such an intervention. • Improve service links, communication and effective practice The proposal is fully supported by all regional partners including all four Local Authorities, OPCC and the two Health Boards. These service links are essential to the success of the pilot in terms of integration into referral pathways, social services assessments and the sharing and promotion of best practice modelling. The safety considerations around the pilot has been carefully thought through, in line with the WG Perpetrator Standards, and includes gaining valuable information from DPP. Communication of the intervention has been supported via the Regional Partnership and will be further promoted with a press release communicated across the whole region. The interventions will be delivered by the commissioned specialist services within MWW, who are part of the larger Regional Partnership and Regional Providers Forum. Best Practice and lessons learned form the pilots will be evidenced in the evaluations and shared via the Regional Partnership and wider forums to inform practice across the Region. • Develop a skilled and resilient workforce The delivery of these interventions has been supported by specific training delivered to the staff who will be working on the projects. This training includes specific delivery from the Intervention Hub on the Perpetrator Intervention they will be delivering, expert insight and input from FPUK and Jane Monkton-Smith and specific risk management from Threshold DAS. The experience gained, in this specialist form of intervention, by the staff teams delivering the interventions is priceless. This investment will strengthen the workforce within the specialist services, in order to support sustainability of the project and improve our regional offer of early intervention and prevention based services.

- Has the grant met the Evidenced Needs for perpetrator services

• What is the identified need The identified need is as explained above. The Regional VAWDASV Strategy, informed by the needs assessment, identifies the need for a consistent availability of perpetrator intervention across the Region. Previously there was only one Respect Accredited Programme delivered in the whole MWW. This is not reflective of the need and diversity of the communities within the region, including the barriers of rurality and dispersed communities. DHRs conducted across the Region evidence this lack of provision and have identified specific opportunities where an offer of such an intervention was missed on several occasions due to lack of availability. In Mid and West Wales, where the barriers due to rurality are prevalent, we need to be innovative and creative in the delivery of these interventions to ensure delivery is both successful and accessible. • How will the Regional Perpetrator Services Revenue Grant address the need? The Regional Grant is addressing this need by continuing the provisions piloted across the region within the last financial year. This will not only offer access to interventions aimed at addressing abusive behaviour but that also addressed the barriers of rurality. The interventions will be delivered both virtually and face to face where this is safe and appropriate. This will allow delivery and access to intervention across the region and ensure we have a consistent and preventative approach region wide. • What research has the organisation undertaken to identify the need? - Stalking intervention Pilot- evaluated by Professor jane Monkton-Smith and in partnership with Forensic Psychology UK - Intervention Hub Pilot- based on psychometric testing and piloted with specialist service providers - Choices Programme evaluation and experience of delivery for a significant period of time, with in Respect accreditation Without this investment we would have risked losing the momentum and development of work over the past year. We would not have been able to sustain this regional offer of intervention and our aim to improve preventative service provision will not be achieved. This project provides value for money by investing in a Regional Provision of intervention that spans four local authority areas. Value for money is also achieved as we have already invested significantly in the design and development of specific interventions and the upskilling of staff teams across the region. These interventions are also eliminating the typically high costs associated with delivering services in rural areas, by reducing costs associated with staff travel, service users accessing the service and venues for face to face delivery. Lastly the project focusses on early intervention and prevention, offering this intervention to address abusive behaviour aims to limit the impact on statutory and specialist services in the long run.

- Please explain how partnership working has been managed and duplication of work for perpetrator services has been avoided (In order to ensure they are safe, effective and evidence-based it is important that perpetrator services are compliant with the Welsh Government Perpetrator Services Standards).

The project forms part of the Mid and West Wales Regional Delivery plan for 2021-22. This is fully supported by the regional partnership members and need evidenced by the regional needs assessment and Regional Strategy. Partnership working is evident throughout the project delivery, as indicated above and also via the strong service links between the Specialist Services delivering the programmes, external professionals and the Regional Adviser. Progress of the programme delivery will feed directly back into the work of the Regional Partnership, Commissioning Activity Planning for the Region and sharing of best practice modelling via the Regional Providers Forum. The regional strategy highlights the lack of provision for perpetrators across the region, therefore the risk of duplication is not relevant. • Choices Programme is accredited by Respect • We have worked with the Intervention Hub and the key partners to establish how the pilot meets the requirements of the WG Standards- document attached. • The stalking intervention is delivered under Forensic Psychology Standards which meet the accreditation requirements.

PLEASE ONLY COMPLETE THE FOLLOWING TABLES THAT RELATE TO YOUR DELIVERY PLAN?

- Please provide a breakdown of exactly how the grant money has been spent for perpetrator services

| Activity | Funding from VAWDASV Grant |  | If not 100% VAWDASV Grant state other funding and source |  | Total |
| --- | --- | --- | --- | --- | --- |
|  | £ | % | £ | % |  |
| Licensing costs | £15,000 | 100% |  |  | £15,000 |
| Staffing costs | £5,437.50 | 100% |  |  | £5,437.50 |
| Staffing Costs | £2,377.50 | 100% |  |  | £2,377.50 |

- Please provide a breakdown of additional targets for perpetrator services

| If applicable - people accessing the service directly |  |  |
| --- | --- | --- |
| Target Group | Breakdown by high/medium/low risk | Total anticipated number of beneficiaries in 2021 - 22 |
| Women | 35 |  |
| Men | 39 |  |
| Not Specified/prefer not to say |  |  |
| Children |  |  |
| TOTALS | 74 |  |

- CLAIM INFORMATION:

- Provide details of actual expenditure in relation to ANNEX A: Perpetrator Services element of the Welsh Government VAWDASV Grant [Note: this information should reflect the breakdown of costs set out in Annex A]

| Activity | Level of cost of activity (forecast spend) | Level of funding from VAWDASV Grant |  |  |  | Funding from other sources: source and amount | Total actual spend to date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Period 1 £ | Period 2 £ | Period 3 £ | Period 4 £ |  |  |
| Staff costings | £7,815 | £5,437.50 | £2,377.50 |  |  |  | £7,815 |
| Licensing Costs | £15,000 | £15,000 |  |  |  |  | £15,000 |
| Totals | £22,815 | £15,000 |  |  |  |  | £22,815 |

- Please update your indicative spend profile for the level of grant awarded:

| Period | Indicative Spend | Actual Spend |
| --- | --- | --- |
| Period 1: April to June | £15,000 | £20,437.50 |
| Period 2: July to September | £1,953.75 | £2,377.50 |
| Period 3: October to December | £1,953.75 |  |
| Period 4: January to March | £1,953.75 |  |
| Total Spend: |  | £22,815 |

- GRANT CLAIM

| - TOTAL GRANT ALLOCATION APPROVED: |  |  |  |  |
| --- | --- | --- | --- | --- |
| FINANCIAL YEAR 2021 - 2022 | (Apr-Jun) £ | (Jul-Sept) £ | (Oct – Dec) £ | (Jan-Mar) £ |
| AMOUNT CLAIMED TO DATE | £20,437.50 | £2,377.50 |  |  |
| CUMULATIVE AMOUNT CLAIMED TO DATE | £20,437.50 | £22,815 |  |  |

| FORECAST EXPENDITURE FOR FY 2021 - 22 | £22,815 |
| --- | --- |
| GRANT STILL OUTSTANDING / UNDERSPEND FORECAST: | £ |

- If there is underspend, please provide an explanation as to how this has occurred and any proposals for reallocating the funding.

- Provide an update on the

| Priority Area | DELIVERY of each of the applicable Priority Areas delivered by your Regional Partnership | Progress made towards the EXIT STRATEGY for each area Delivered |
| --- | --- | --- |
| Services that are preventative or support victims and survivors of domestic abuse | Our proposal was to extend the increased capacity enabled by the Revenue Grant awarded in 2020-21. The allocation will increase the capacity within all existing VAWDASV specialist services across the region. This will mean increased capacity for the staffing teams across the eight specialist VAWDASV providers in delivering: specialist counselling, one to one support, refuge and floating support specific provision and increased capacity within the Regional IDVA service. This will also support the increased management functions, purchase of IT equipment to support increased capacity where required and specific case management functions across all the specialist service providers, in order to release capacity for specialist staff to deliver provision. | Our regional funding as been allocated equally across our Regional Specialist providers to increase capacity as outlined. This includes resourcing increased capacity across all areas of need identified in our proposed delivery, via our specialist services. |
| Services that are preventative or support children and young people suffering domestic abuse and sexual violence | The increase in service capacity mentioned above includes specific increase in support hours for Children and Young People. This will increase the hours of support available across the region to support CYP within schools, one to one and via holistic family support. The hours will be increased within the existing specialist services who deliver specialist intervention for CYP. This will also include increased capacity within the Spectrum team across the region and following school closures, the Spectrum team will offer online support sessions to primary and secondary school pupils, responding to Police and Operation Encompass Information on Domestic Abuse Incidents. |  |
| Services that are preventative or or support older people suffering domestic abuse and sexual violence | The increase in capacity across our specialist services will include support for older people suffering abuse. This is inclusive of support specific to older victims of VAWDASV. All of the commissioned service providers are committed to inclusive provision of support that is tailored to individual need, including the specific needs of older people. This service provision is across refuge, dispersed accommodation and community based provision and also includes dedicated older persons support programmes designed by the specialist providers. |  |
| Services that are preventative of or support victims and survivors of sexual violence | We are working with Newpathways to increase the capacity of the existing sexual violence services across the region. This will be used specifically to increase the capacity of existing specialist SV counselling in order to reduce the back-log and waiting lists for this support, and increase the capacity for new and increased demand in cases following ease in lock-down measures. The allocation of funding to Newpathways will also facilitate specific case management functions across the region to ensure response to referrals is seamless and efficient. |  |
| Services that are preventative or or support victims and survivors of Honour Based Abuse, including FGM and Forced Marriage | We will be expanding on the existing services that deliver specialist VAWDASV provision across the region. This will be delivered via the existing specialist service providers who also provide support to victims of HBV across Mid and West Wales. |  |
| Additional resources to reduce backlogs and free up capacity for those needing urgent support | As discussed previously, we have waiting lists for some of our specialist services and interventions within the region. With the demand for services increasing, and this demand anticipated to grow. We are allocating resource to reduce and clear these back-logs in-order to increased capacity for services to be able to meet demand as it presents. Ensuring support is timely and relevant to individuals on their journey to recovery. This will be relevant to all specialist services but more specifically for the sexual violence counselling provision. |  |
| Support for VAWDASV service providers to prepare for and meet additional demand for support, including taking precautions against the spread of Covid-19 | The demand for specialist VAWDASV Service provision across Mid and West Wales has significantly increased following lockdown. We are facing the increase of demand due to an anticipated increase in domestic violence cases during the period of lockdown, increased in complexity and severity of abuse suffered and the delay in accessing support due to the impact of lock-down. Our allocation of the regional funding will be targeted at ensuring the specialist providers are best equipped to be able to respond to this demand in the most appropriate way. |  |

- Please provide a breakdown of exactly how the grant money has been spent on Annex B: NEEDS BASED Activity

| Priority Area and Organisation claiming expenditure | Funding from VAWDASV Grant |  | If not 100% VAWDASV Grant state other funding and source |  | Total |
| --- | --- | --- | --- | --- | --- |
|  | £ | % | £ | % |  |
| 1,2,3,5,7,9,10- Carmarthenshire DAS | £4,125 | 100% |  |  | £4,125 |
| 1,2,3,5,7,9,10- Pobl | £4,903.02 | 100% |  |  | £4,903.02 |
| 1,2,3,5,7,9,10- West Wales DAS | £13,035.60 | 100% |  |  | £13,035.60 |
| 1,2,3,5,7,8, 9,10- -Hafan Cymru | £12,388.62 | 100% |  |  | £12,388.62 |
| 1,2,3,5,7,8, 9,10- Threshold DAS | £6,194.32 | 100% |  |  | £6,194.32 |
| 1,2,3,4,5,7,9,10- New Pathways | £22,625 | 100% |  |  | £22,625 |
| 1,2,3,5,7,8, 9,10- MFCC | £12,388.62 | 100% |  |  | £12,388.62 |
| 1,2,3,5,7,8, 9,10- Calan DVS | £6,258.08 | 100% |  |  | £6,258.08 |
| Total |  |  |  |  | £81,918.26 |

- Please provide a breakdown of additional targets for Annex B Needs Based services

| If applicable - people accessing the service directly |  |  |
| --- | --- | --- |
| Target Group | Breakdown by high/medium/low risk | Total anticipated number of beneficiaries in 2021 - 22 |
| Women | 66 |  |
| Men | 12 |  |
| Not Specified/prefer not to say | 94 |  |
| Children | 110 |  |
| TOTALS | 282 |  |

- CLAIM INFORMATION:

- Provide details of actual expenditure in relation to Annex B: NEEDS BASED element of the Welsh Government VAWDASV Grant [Note: this information should reflect the breakdown of costs set out in Annex B]

| Activity | Level of cost of activity (forecast spend) | Level of funding from VAWDASV Grant |  |  |  | Funding from other sources: source and amount | Total actual spend to date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Period 1 £ | Period 2 £ | Period 3 £ | Period 4 £ |  |  |
| Carms DAS | £24,777.25 | £6,187.50 | £6,187.50 | £4,125 |  |  | £16,500 |
| Pobl | £24,777.25 | £9,624.62 | £10,249.61 | £4,903.02 |  |  | £24,777.25 |
| WWDAS | £24,777.25 | £5,686 |  | £13,035.60 |  |  | £18,721.60 |
| Newpathways | £24,777.25 |  |  | £22,625 |  |  | £22,625 |
| Hafan Cymru | £24,777.25 |  | £6,194.31 | £12,388.62 |  |  | £18,582.93 |
| Threshold DAS | £24,777.25 | £6,194.32 | £6,194.32 | £6,194.32 |  |  | £18,582.96 |
| MFCC | £24,777.25 | £6,194.31 |  | £12,388.62 |  |  | £18,582.93 |
| Calan DVS | £24,777.25 | £6,000 | £6,259.08 | £6,258.08 |  |  | £18,517.16 |
| Totals | £198,218 | £39,886.75 | £35,084.82 | £81,918.26 |  |  | £156,889.83 |

- Please update your indicative spend profile for the level of grant awarded:

| Period | Indicative Spend | Actual Spend |
| --- | --- | --- |
| Period 1: April to June | £49,554.5 | £39,886.75 |
| Period 2: July to September | £49,554.5 | £35,084.82 |
| Period 3: October to December | £49,554.5 | £81,918.26 |
| Period 4: January to March | £49,554.5 |  |
| Total Spend: |  | £156,889.83 |

- GRANT CLAIM

| - TOTAL GRANT ALLOCATION APPROVED – NEEDS BASED: |  |  |  |  |
| --- | --- | --- | --- | --- |
| FINANCIAL YEAR 2021 - 2022 | (Apr-Jun) £ | (Jul-Sept) £ | (Oct – Dec) £ | (Jan-Mar) £ |
| AMOUNT CLAIMED TO DATE | £39,886.75 | £35,084.82 | £81,918.26 |  |
| CUMULATIVE AMOUNT CLAIMED TO DATE | £39,886.75 | £74,971.57 | £156,889.83 |  |

| FORECAST EXPENDITURE FOR FY 2021 - 22 | £198,218 |
| --- | --- |
| GRANT STILL OUTSTANDING / UNDERSPEND FORECAST: | £ |

- If there is underspend, please provide an explanation as to how this has occurred and any proposals for reallocating the funding.

| Provide an update on the |  |  |
| --- | --- | --- |
| Priority Area | DELIVERY of each of the applicable Areas delivered by your Regional Partnership | Progress made towards the EXIT STRATEGY for each area Delivered |
| - Services that support the MARAC Infrastructure |  |  |
| - Community Communication Group | We have established and delivered the Regional Communications Campaign targeting the beauty industry, this ran alongside National Safeguarding Week and included; - Live and pre-recorded VAWDASV Awareness Training sessions - Pod Cast - Dissemination of Live Fear Free Materials across participating establishments | NA |
| - Communications to promote Remote Hearing Sits MID AND WEST WALES ONLY | Building works have commenced on site and we are on schedule for completion by the end of March 2022. | NA |

Please provide a breakdown of exactly how the grant money has been spent on Annex C: COVID 19 Restart Activity - We have not received all invoices for the Communications work (£6,000) yet. - The work around the remote evidence site has included work to establish robust connectivity at the site and has also included purchase of relevant equipment and IT storage.

| Priority Area and Organisation claiming expenditure | Funding from VAWDASV Grant |  | If not 100% VAWDASV Grant state other funding and source |  | Total |
| --- | --- | --- | --- | --- | --- |
|  | £ | % | £ | % |  |
| Beauty Industry Campaign | £350 | 100% |  |  | £4,219.60 |
|  | £300 |  |  |  |  |
|  | £243.75 |  |  |  |  |
|  | £3,325.85 |  |  |  |  |

Please provide a breakdown of additional targets for Annex B Needs Based services

| If applicable - people accessing/benefited from the service directly |  |  |
| --- | --- | --- |
| Target Group | Breakdown by high/medium/low risk | Total anticipated number of beneficiaries in 2021 - 22 |
| Women |  |  |
| Men |  |  |
| Not Specified/prefer not to say |  |  |
| Children |  |  |
| TOTALS |  |  |

- CLAIM INFORMATION:

Provide details of actual expenditure in relation to Annex C: COVID 19 Restart element of the Welsh Government VAWDASV Grant [Note: this information should reflect the breakdown of costs set out in Annex C)

| Activity | Level of cost of activity (forecast spend) | Level of funding from VAWDASV Grant |  |  |  | Funding from other sources: source and amount | Total actual spend to date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Period 1 £ | Period 2 £ | Period 3 £ | Period 4 £ |  |  |
| Beauty Industry Campaign | £6,000 |  |  | £350 |  |  | £350 |
|  |  |  |  | £300 |  |  | £300 |
|  |  |  |  | £243.75 |  |  | £243.75 |
|  |  |  |  | £3,325.85 |  |  | £3,325.85 |
| Totals |  |  |  | £4,219.60 |  |  |  |

- Please update your indicative spend profile for the level of grant awarded:

| Period | Indicative Spend | Actual Spend |
| --- | --- | --- |
| Period 1: April to June |  |  |
| Period 2: July to September | 8,622.94 | £3,769 |
| Period 3: October to December | 8,622.94 | £4,219.60 |
| Period 4: January to March | 8,622.94 |  |
| Total Spend: |  | £7,988.60 |

- GRANT CLAIM

| - TOTAL GRANT ALLOCATION APPROVED – Covid 19 Restart: |  |  |  |  |
| --- | --- | --- | --- | --- |
| FINANCIAL YEAR 2021 - 2022 | (Apr-Jun) £ | (Jul-Sept) £ | (Oct – Dec) £ | (Jan-Mar) £ |
| AMOUNT CLAIMED TO DATE |  | £3,769 | £4,219.60 |  |
| CUMULATIVE AMOUNT CLAIMED TO DATE |  | £3,769 | £7,988.60 |  |

| FORECAST EXPENDITURE FOR FY 2021 - 22 | £25,868.84 |
| --- | --- |
| GRANT STILL OUTSTANDING / UNDERSPEND FORECAST: | £ |

- If there is underspend, please provide an explanation as to how this has occurred and any proposals for reallocating the funding.

Please enter the amount that you are claiming for this period:

| Activity | Total Claim made this period |
| --- | --- |
| Core Delivery Plan (including needs based 4%) | £92,150 |
| Annex A: Perpetrator Funding |  |
| Annex B: Needs Based Covid-19 | £81,918.26 |
| Annex C: Covid 19 Restart | £4,219.60 |
| Total to be paid | £178,287.86 |

- Provide an update on the development of the regional governance structures

The above diagram outlines the governance arrangements around our Regional Partnership.

- Provide an update on how links have been made with other cross-cutting governance, service planning and commissioning arrangements

- Regional Partnership Boards and Public Service Boards- As Regional Adviser I have made links with the representatives for both RPBs and PSBs which allows opportunities for us to identify commonalities in work under both agendas and possibilities for collaboration in terms of resource. This is still an area in need of improvement as we do not work as closely as I feel we could, I have raised this with WG at the National Strategy Review meetings. - The HSCG- HSG- Representation from this board sits on the Regional VAWDASV Board. As regional Adviser I also sit on the HSCG group to ensure co-ordination of work is consistent and aligns with the work of the regional VAWDASV strategy. - The DCI leading on VAWDASV for Dyfed Powys Police is the Chair of the VAWDASV Strategic Board and the Director of Commissioning for the Police and Crime Commissioner sits on the VAWDASV Strategic Board. - The Regional Adviser reports directly into the Local Criminal Justice Board in order to ensure that the priorities of the LCJB are represented at the VAWDASV Board. I also report directly to the CJIW Board to provide full updates in relation to the Remote Evidence Site implementation across Wales. - The Regional Advisor attends the Regional Specialist Service Providers Forum routinely to provide update and facilitate consultation on the work under the regional strategy.

- Provide an update on any sub groups that support the Governance structure

The key subgroups under the MWW Strategy are; • Survivor Engagement and Communication - TOR established - Updated membership - Revised action plan • Priority 2 Subgroup - LA Education points of contact have been ideitnifed - This will include specialist services and TAF teams - Focus will be on response to RSE curriculum • Priority 3 Subgroup Holding Perpetrators to account - This subgroup is well established and oversees the work under priority 3 - This includes the Regional Offer of intervention • Training Subgroup - All relevant authorities and specialist providers are members of this well-established subgroup. - Monitoring delivery of 2021-22 Delivery Plan • VAWDASV Commissioning Subgroup - Commissioning Subgroup and membership established with TOR - Regional Service Specification is now complete - Regional Action Plan to focus on implementation

- Provide an update on the risks identified in the delivery plan

None identified

I hereby make application on behalf of the Regional Partnership for grant payable under the Welsh Government’s grant scheme in relation to violence against women, domestic abuse and sexual violence services. I certify that to the best of my knowledge and belief:

a)	the information given is correct and no other Exchequer specific grants or contributions have been or will be made towards the Project related expenditure detailed in this claim;

- the grant claimed is within the agreed expenditure limits; and

- All expenditure within this claim has been defrayed and the appropriate full audit trail (where applicable - receipts, payroll evidence, timesheets, invoices etc.) has been checked and approved by the relevant certifier within the Regional Partnership.

| Signature | Date 14.01.22 |
| --- | --- |
| Name (Printed): Cathy Richards | Position: Senior Safeguarding Manager |

Welsh Government use only I confirm that I have examined the above and am content to certify that the expenditure claimed is in accordance with the agreed delivery plan and any amendments agreed thereafter; and that these costs have not been previously reimbursed and the balance of grant claimed should be authorised immediately.

Signature:

Name (Printed):

Date